URITHI

Your Legacy, Protected Forever

APPLICATION PROJECT PLAN

Version 1.0  |  April 2026  |  Confidential

| Project URITHI Platform v1.0 | Project Manager Primo (Founder & CEO) |
| --- | --- |
| Start Date April 2026 | Target Launch October 2026 (Month 6) |
| Status In Planning | Platform Web + Mobile + Cloud |

# 1. Project Overview

## 1.1 Project Summary

URITHI is Uganda's first purpose-built trust management platform — a multi-tenant SaaS application that digitises and automates the complete lifecycle of family trust administration. This project plan covers the full development, testing, deployment, and launch of URITHI version 1.0, from initial setup through to the first 10 paying law firm clients.

Project Mission To build, launch, and grow a production-ready trust management platform that protects Ugandan family wealth across generations — delivered within 12 months from project start, reaching break-even by Month 7 with 10 paying clients by Month 12.

## 1.2 Project Objectives

- Deliver a fully functional web and mobile trust management platform by Month 6

- Onboard 3 pilot law firms in Kampala for free beta testing by Month 4

- Achieve first paying client conversion by Month 7

- Reach 10 paying clients and UGX 14.7M MRR by Month 12

- Complete URA tax filing integration and blockchain audit trail by Month 9

- Prepare platform for East Africa expansion by Month 12

## 1.3 Project Scope

### In Scope

- FastAPI Python backend API with PostgreSQL database

- React TypeScript web application — trustee dashboard

- React Native mobile app — beneficiary portal (iOS and Android)

- Document vault with SHA-256 encryption and hash verification

- Mobile Money integration via Africa's Talking (MTN and Airtel Uganda)

- Multi-signature distribution approval workflow

- URA tax filing engine with auto-populated returns

- URSB registration workflow integration

- Hyperledger Fabric blockchain audit trail

- Celery task scheduler for automated distributions

- Marketing website at urithi.io (Next.js + TailwindCSS)

- Admin super-dashboard for platform management

### Out of Scope (Phase 1)

- Kenya, Tanzania, and Rwanda localisation (Phase 4)

- Native iOS and Android apps (React Native covers both — native apps are Phase 3)

- AI-powered document analysis (future roadmap)

- Integration with Uganda Stock Exchange for share tracking (Phase 2)

- Public API for third-party integrations (Phase 3)

## 1.4 Project Assumptions

- Seed funding of UGX 500M (~$130,000) is secured or self-funded from savings before Month 3

- NITA-U API credentials for URA e-Tax integration are obtainable within 6 months

- Africa's Talking Uganda Mobile Money API access is approved within 2 weeks of application

- AWS cloud infrastructure is used for hosting — budget of UGX 1M/month for cloud costs

- At least 3 Kampala law firms agree to pilot URITHI for free during Months 3–6

- The founder (Primo) is the primary developer for the first 6 months

## 1.5 Project Constraints

- Budget constraint: Development must operate within UGX 500M seed funding envelope

- Time constraint: Paid launch must happen by Month 7 to hit break-even targets

- Resource constraint: Solo founder development until Month 6 when second developer hired

- Regulatory constraint: URA and URSB API access depends on government timelines outside project control

- Connectivity constraint: Platform must function on low-bandwidth Uganda internet — offline capability required for mobile app

# 2. Work Breakdown Structure (WBS)

The URITHI project is broken into 8 major work packages, each containing specific deliverables and tasks. Every task has a defined owner, estimated effort, and dependency chain.

## 2.1 WP1 — Project Setup and Infrastructure

| Task | Owner | Effort | Month |
| --- | --- | --- | --- |
| Register URITHI Technologies Ltd with URSB | Primo | 1 day | Month 1, Week 1 |
| Register with URA — obtain company TIN | Primo | 1 day | Month 1, Week 1 |
| Open Stanbic business bank account | Primo | 1 day | Month 1, Week 1 |
| Purchase domain urithi.io on Namecheap | Primo | 1 hour | Month 1, Week 1 |
| Set up AWS account and IAM roles | Primo | 4 hours | Month 1, Week 1 |
| Set up GitHub organisation (urithi-platform) | Primo | 2 hours | Month 1, Week 1 |
| Configure GitHub Actions CI/CD pipeline | Primo | 1 day | Month 1, Week 2 |
| Set up AWS RDS PostgreSQL 16 instance | Primo | 4 hours | Month 1, Week 2 |
| Set up AWS S3 bucket for document storage | Primo | 2 hours | Month 1, Week 2 |
| Set up Redis on AWS ElastiCache for Celery | Primo | 2 hours | Month 1, Week 2 |
| Configure environment variables and secrets manager | Primo | 4 hours | Month 1, Week 2 |
| Apply for Africa's Talking Uganda API access | Primo | 2 hours | Month 1, Week 1 |

## 2.2 WP2 — Backend API Development (Python + FastAPI)

| Task | Owner | Effort | Month |
| --- | --- | --- | --- |
| Set up FastAPI project structure and Uvicorn | Primo | 1 day | Month 1, Week 2 |
| Build authentication service (JWT + MFA + bcrypt) | Primo | 3 days | Month 1, Week 3 |
| Implement multi-tenant middleware and RBAC | Primo | 2 days | Month 1, Week 3 |
| Build trust CRUD endpoints with Pydantic validation | Primo | 3 days | Month 1, Week 4 |
| Build beneficiary management endpoints | Primo | 2 days | Month 2, Week 1 |
| Build asset registry endpoints | Primo | 2 days | Month 2, Week 1 |
| Build document upload with SHA-256 hashing | Primo | 3 days | Month 2, Week 2 |
| Build distribution engine with condition evaluator | Primo | 4 days | Month 2, Week 2-3 |
| Build multi-signature approval workflow | Primo | 3 days | Month 2, Week 3 |
| Build URA tax calculation engine | Primo | 4 days | Month 2, Week 4 |
| Implement audit log middleware (append-only) | Primo | 2 days | Month 3, Week 1 |
| Set up Celery workers and beat scheduler | Primo | 2 days | Month 3, Week 1 |
| Write Alembic database migrations | Primo | 2 days | Month 3, Week 2 |
| Write pytest test suite (80%+ coverage) | Primo | 5 days | Month 3, Week 2-3 |
| API documentation review via Swagger /docs | Primo | 1 day | Month 3, Week 3 |

## 2.3 WP3 — Database Design and Implementation

| Task | Owner | Effort | Month |
| --- | --- | --- | --- |
| Design and implement multi-tenant schema | Primo | 2 days | Month 1, Week 3 |
| Implement Row Level Security policies | Primo | 1 day | Month 1, Week 3 |
| Create all core tables (trusts, beneficiaries, etc.) | Primo | 2 days | Month 1, Week 4 |
| Create append-only audit log with delete rule | Primo | 1 day | Month 2, Week 1 |
| Create all performance indexes | Primo | 4 hours | Month 2, Week 1 |
| Seed database with test data for development | Primo | 1 day | Month 2, Week 2 |
| Configure automated daily backups on AWS RDS | Primo | 4 hours | Month 2, Week 2 |
| Performance testing and query optimisation | Primo | 2 days | Month 3, Week 4 |

## 2.4 WP4 — Frontend Web Application (React + TypeScript)

| Task | Owner | Effort | Month |
| --- | --- | --- | --- |
| Set up React + TypeScript + Vite project | Primo | 1 day | Month 2, Week 1 |
| Configure TailwindCSS with URITHI design tokens | Primo | 1 day | Month 2, Week 1 |
| Build API service layer (Axios + interceptors) | Primo | 2 days | Month 2, Week 2 |
| Build authentication flows (login, MFA, logout) | Primo | 2 days | Month 2, Week 2 |
| Build main trustee dashboard screen | Primo | 3 days | Month 2, Week 3 |
| Build trust setup and configuration wizard | Primo | 3 days | Month 2, Week 3-4 |
| Build beneficiary management screen | Primo | 2 days | Month 2, Week 4 |
| Build asset registry screen | Primo | 2 days | Month 3, Week 1 |
| Build document vault screen with upload and preview | Primo | 3 days | Month 3, Week 1-2 |
| Build distribution approval workflow screen | Primo | 3 days | Month 3, Week 2 |
| Build URA tax filing screen | Primo | 3 days | Month 3, Week 3 |
| Build audit trail and compliance screen | Primo | 2 days | Month 3, Week 3 |
| Implement Redux state management | Primo | 2 days | Month 3, Week 4 |
| Cross-browser testing and responsive design QA | Primo | 2 days | Month 4, Week 1 |

## 2.5 WP5 — Mobile Application (React Native + Expo)

| Task | Owner | Effort | Month |
| --- | --- | --- | --- |
| Set up React Native + Expo project | Primo | 1 day | Month 3, Week 2 |
| Build beneficiary login and onboarding flow | Primo | 2 days | Month 3, Week 3 |
| Build beneficiary home screen (payments, balance) | Primo | 3 days | Month 3, Week 4 |
| Build payment history screen | Primo | 2 days | Month 4, Week 1 |
| Build conditions and entitlements screen | Primo | 2 days | Month 4, Week 1 |
| Implement offline data sync with SQLite/WatermelonDB | Primo | 3 days | Month 4, Week 2 |
| Implement push notifications (Expo Notifications) | Primo | 2 days | Month 4, Week 2 |
| Test on Android and iOS devices | Primo | 3 days | Month 4, Week 3 |
| Submit to Google Play Store (Android) | Primo | 2 days | Month 5, Week 2 |
| Submit to Apple App Store (iOS) | Primo | 2 days | Month 5, Week 3 |

## 2.6 WP6 — Integrations

| Task | Owner | Effort | Month |
| --- | --- | --- | --- |
| Africa's Talking SMS integration | Primo | 1 day | Month 2, Week 3 |
| Africa's Talking Mobile Money B2C payments | Primo | 3 days | Month 3, Week 1 |
| MTN and Airtel network prefix detection | Primo | 1 day | Month 3, Week 1 |
| URA e-Tax API integration (TIN verification) | Primo | 5 days | Month 5, Week 1-2 |
| URA tax return auto-submission endpoint | Primo | 3 days | Month 5, Week 2-3 |
| URSB registration workflow integration | Primo | 4 days | Month 5, Week 3-4 |
| Resend transactional email integration | Primo | 1 day | Month 2, Week 4 |
| AWS S3 encrypted document storage pipeline | Primo | 2 days | Month 2, Week 3 |
| Hyperledger Fabric blockchain node setup | Primo | 5 days | Month 6, Week 1-2 |
| Blockchain chaincode deployment and testing | Primo | 3 days | Month 6, Week 2-3 |

## 2.7 WP7 — Marketing Website

| Task | Owner | Effort | Month |
| --- | --- | --- | --- |
| Set up Next.js 14 + TailwindCSS project | Primo | 4 hours | Month 1, Week 3 |
| Build homepage with hero, features, pricing CTA | Primo | 3 days | Month 1, Week 3-4 |
| Build product features page | Primo | 2 days | Month 1, Week 4 |
| Build pricing page with tier comparison | Primo | 1 day | Month 2, Week 1 |
| Build about page with mission and founder story | Primo | 1 day | Month 2, Week 1 |
| Build blog with MDX and first 3 SEO articles | Primo | 4 days | Month 2, Week 2 |
| Build demo booking page with Cal.com embed | Primo | 1 day | Month 2, Week 2 |
| Deploy to Vercel with custom domain urithi.io | Primo | 4 hours | Month 2, Week 2 |
| Set up Google Search Console and Analytics | Primo | 2 hours | Month 2, Week 3 |
| Create Uganda Family Trust Guide PDF lead magnet | Primo | 3 days | Month 2, Week 3-4 |

## 2.8 WP8 — Testing, Security, and Launch

| Task | Owner | Effort | Month |
| --- | --- | --- | --- |
| Full end-to-end integration testing | Primo | 5 days | Month 4, Week 3-4 |
| Security penetration testing (OWASP Top 10) | Primo + contract | 3 days | Month 4, Week 4 |
| Load testing with Locust (simulate 500 users) | Primo | 2 days | Month 5, Week 1 |
| UAT with 3 pilot law firms | Primo + pilots | 4 weeks | Month 4 full |
| Bug fixes from UAT feedback | Primo | 2 weeks | Month 5, Week 1-2 |
| Configure AWS CloudWatch monitoring and alerts | Primo | 1 day | Month 5, Week 3 |
| Set up error tracking with Sentry | Primo | 4 hours | Month 5, Week 3 |
| Data Protection and Privacy Act compliance review | Primo + legal | 2 days | Month 5, Week 4 |
| Prepare onboarding materials and video walkthroughs | Primo | 3 days | Month 5, Week 4 |
| Paid launch — convert pilots to paying clients | Primo | 1 week | Month 6, Week 4 |

# 3. Project Schedule — 12-Month Timeline

The URITHI project runs across 12 months from April 2026. The first 6 months focus on building and testing. Month 7 is the paid launch. Months 8–12 focus on growth, scaling, and feature expansion.

## 3.1 Phase 1 — Build (Months 1–3)

Phase 1 Goal Complete the core backend API, database, and basic frontend. Register the company. Apply for all required API credentials. Have a working internal demo by end of Month 3.

| Month | Key Deliverables | Milestone | Success Metric |
| --- | --- | --- | --- |
| Month 1 | Company registered. AWS infrastructure live. FastAPI skeleton. Database schema complete. Marketing website launched. | Infrastructure ready | urithi.io live. AWS running. |
| Month 2 | Backend API 60% complete. Auth, trust, beneficiary, and asset endpoints done. Mobile Money SMS live. React frontend started. | API functional | All core endpoints tested via Swagger. |
| Month 3 | Full backend API complete. Distribution engine live. All frontend screens built. Internal demo ready. First pilot law firm approached. | Internal demo | Full demo walkthrough completed internally. |

## 3.2 Phase 2 — Pilot (Months 4–5)

Phase 2 Goal Onboard 3 pilot law firms for free. Conduct user acceptance testing. Fix all critical bugs. Complete mobile app. Prepare for paid launch.

| Month | Key Deliverables | Milestone | Success Metric |
| --- | --- | --- | --- |
| Month 4 | 3 pilot law firms onboarded. UAT begins. Mobile app iOS and Android builds complete. Security testing done. | Pilots live | 3 firms actively using platform. |
| Month 5 | UAT feedback collected and bugs fixed. URA API integration live. Mobile apps submitted to stores. Onboarding materials ready. | Launch ready | Zero critical bugs. Apps approved. |

## 3.3 Phase 3 — Launch (Month 6–7)

Phase 3 Goal Convert 3 pilot firms to paid subscribers. Launch publicly. Present at Uganda Law Society. First paying revenue received. Break-even achieved by Month 7.

| Month | Key Deliverables | Milestone | Success Metric |
| --- | --- | --- | --- |
| Month 6 | Blockchain audit trail deployed. All integrations live. Full platform production-ready. Public launch event. Pilot firms converted to paid. | Public launch | 3 paying clients. First UGX 4.5M MRR. |
| Month 7 | Referral programme launched. Uganda Law Society Conference presentation. Cold outreach to 50 law firms. New client onboardings. | Break-even | Revenue covers monthly costs. |

## 3.4 Phase 4 — Growth (Months 8–12)

Phase 4 Goal Scale to 10 paying clients. Hire second developer. Complete URA and URSB full API integration. Approach Stanbic Bank Enterprise contract. Begin Kenya market research.

| Month | Key Deliverables | Milestone | Success Metric |
| --- | --- | --- | --- |
| Month 8 | Hire second developer. Smart contract distributions live. 6 paying clients. First Enterprise conversation with Stanbic Bank. | Team grows | 6 clients. UGX 8M MRR. |
| Month 9 | URSB registration workflow fully automated. 8 paying clients. Seed funding round closes. URITHI Academy content started. | Seed closed | 8 clients. Funding secured. |
| Month 10 | First Enterprise bank pilot (Stanbic or DFCU). 9 paying clients. Kenya market research report completed. | Enterprise pilot | 9 clients. Bank pilot signed. |
| Month 11 | 10 paying clients reached. Kenya product localisation begins. Series A preparation. URITHI Academy launches. | 10 clients | UGX 14.7M MRR achieved. |
| Month 12 | Year 1 review and report. Kenya beta launch planning. Year 2 roadmap finalised. Investor update prepared. | Year 1 complete | UGX 176M ARR. Platform stable. |

# 4. Resource Plan

## 4.1 Human Resources

| Role | Name | Start | Responsibilities |
| --- | --- | --- | --- |
| Founder / Lead Developer | Primo | Month 1 | Full-stack development, product, business development, sales |
| Legal Advisor | To recruit | Month 1 | Trust law accuracy, URSB relationships, law firm partnerships |
| Finance Advisor | To recruit | Month 2 | URA tax engine review, financial modelling, CPA oversight |
| Second Developer | To hire | Month 8 | Mobile app, Kenya localisation, feature development |
| Sales Executive | To hire | Month 9 | Law firm outreach, demo calls, contract negotiations |
| Security Tester (contract) | Freelance | Month 4 | Penetration testing, OWASP audit, vulnerability report |

## 4.2 Technology Resources

| Resource | Cost / Month | Purpose |
| --- | --- | --- |
| AWS EC2 (t3.medium) | UGX 145,000 | FastAPI backend application server |
| AWS RDS PostgreSQL (db.t3.small) | UGX 210,000 | Primary database with automated backups |
| AWS S3 (document storage) | UGX 40,000 | Encrypted trust document storage |
| AWS ElastiCache Redis | UGX 80,000 | Celery task queue and session cache |
| Vercel (marketing website) | Free | Next.js marketing site hosting with CDN |
| Africa's Talking SMS + MoMo | Pay per use | SMS notifications and Mobile Money distributions |
| GitHub (Team plan) | UGX 15,000 | Code repository and CI/CD pipeline |
| Sentry (error monitoring) | Free tier | Real-time error tracking and alerts |
| Resend (email) | Free (3K/month) | Transactional emails to trustees and beneficiaries |
| Domain urithi.io | UGX 46,000/year | Primary brand domain |
| Total infrastructure / month | ~UGX 490,000 | Scales with usage — estimate for first 6 months |

## 4.3 Budget Allocation

| Budget Line | Amount (UGX) | % of Seed | Period |
| --- | --- | --- | --- |
| Engineering — Primo salary (12 months) | 200,000,000 | 40% | Months 1–12 |
| Legal setup and advisor fees | 75,000,000 | 15% | Months 1–6 |
| Sales and marketing | 75,000,000 | 15% | Months 4–12 |
| Cloud infrastructure (AWS) | 60,000,000 | 12% | Months 1–12 |
| Operations and administration | 50,000,000 | 10% | Months 1–12 |
| Reserve and contingency | 40,000,000 | 8% | As needed |
| TOTAL SEED BUDGET | 500,000,000 | 100% | 12 months |

# 5. Risk Register

The following risks have been identified, assessed, and mitigated as part of the URITHI project planning process. Risks are rated by likelihood (1–5) and impact (1–5). Risk Score = Likelihood x Impact.

| Risk | Likelihood | Impact | Score | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| Slow law firm adoption | 4 | 5 | 20 — High | 3-month free pilot removes adoption barrier. Uganda Law Society partnership for credibility. Personal founder-led onboarding for each firm. |
| URA / URSB API access delayed | 3 | 4 | 12 — High | Build manual CSV export fallback. Design system to work without API in MVP — add integration in Phase 3. Engage NITA-U from Month 1. |
| Solo founder burnout | 3 | 4 | 12 — High | Ship MVP fast — do not build everything before first client. Outsource security testing. Hire second developer by Month 8. Set clear weekly targets. |
| Funding takes longer to raise | 3 | 5 | 15 — High | Start approaching investors from Month 1. Apply to NITA-U and Founders Factory programmes for non-dilutive funding. Revenue from Month 7 reduces dependence on external funding. |
| Data security breach | 2 | 5 | 10 — Med | Penetration testing before launch. MFA enforcement. End-to-end encryption. Blockchain immutability. Monthly security reviews. Cyber insurance. |
| Mobile Money API downtime | 2 | 3 | 6 — Med | Retry queue with Celery. Support both MTN and Airtel as fallbacks. Bank transfer fallback. Real-time monitoring alerts to trustees. |
| Well-funded competitor enters market | 2 | 4 | 8 — Med | Speed to 10 paying clients creates switching cost moat. Deep URA/URSB/Mobile Money integration is 6–12 month advantage. First-mover brand recognition in Uganda. |
| Uganda Trustees Act regulatory change | 1 | 3 | 3 — Low | Legal advisor monitors all regulatory developments. Rules engine is configurable for rapid compliance updates without full redeployment. |

# 6. Quality Plan

## 6.1 Definition of Done

A feature is only considered complete and deployable when ALL of the following criteria are met:

- Unit tests written and passing with minimum 80% code coverage

- Integration tests passing against staging database

- API endpoints documented in Swagger and manually verified

- Security review completed — no hardcoded secrets, input validation in place

- Frontend component tested across Chrome, Firefox, and Safari

- Mobile app tested on Android (physical device) and iOS (simulator minimum)

- Peer review completed — code reviewed against URITHI coding standards

- Feature deployed to staging environment and smoke-tested

- Product owner (Primo) signed off on acceptance criteria

## 6.2 Testing Strategy

| Test Type | Tool | Coverage |
| --- | --- | --- |
| Unit tests (backend) | pytest | All service layer functions, condition evaluator, tax calculation engine — minimum 80% |
| Integration tests | pytest + httpx | All API endpoints tested against test database — full request/response cycle |
| Frontend component tests | Vitest + RTL | All React components — user interactions, state changes, error states |
| End-to-end tests | Playwright | Critical user journeys — login, create trust, process distribution, file tax return |
| Security / penetration test | OWASP ZAP | OWASP Top 10, SQL injection, XSS, CSRF, authentication bypass — Month 4 |
| Load testing | Locust | Simulate 500 concurrent users — API response time must remain under 500ms |
| UAT (User Acceptance) | Manual — pilot firms | 3 Kampala law firms testing real trust scenarios over 4 weeks — Month 4 |
| Mobile device testing | Physical + Expo | Samsung Galaxy A-series (Android), iPhone 12+ (iOS) — Uganda most common devices |

## 6.3 Code Quality Standards

- Python backend: PEP 8 style guide enforced via flake8 and black formatter

- TypeScript frontend: ESLint with Airbnb configuration. No any types allowed.

- All secrets stored in AWS Secrets Manager — never in code or .env files committed to Git

- All database queries use parameterised inputs — no raw SQL string concatenation

- Every API endpoint requires authentication except /health and /auth/login

- All monetary values stored as integers in UGX (no floating point for money)

- All file uploads virus-scanned before storage via ClamAV

# 7. Communication and Reporting Plan

## 7.1 Internal Reporting Cadence

| Meeting / Report | Frequency | Audience | Content |
| --- | --- | --- | --- |
| Daily standup | Daily (self) | Primo | What was done yesterday, what today, any blockers |
| Weekly progress review | Every Friday | Primo + advisors | Tasks completed vs planned, next week priorities, risks |
| Monthly investor update | Monthly | Investors | MRR, client count, key wins, blockers, next month targets |
| Quarterly milestone review | Quarterly | All stakeholders | Full project health check against plan — timeline, budget, risks |
| Pilot firm feedback session | Bi-weekly | Pilot law firms | Feature feedback, bug reports, usability issues, wishlist |

## 7.2 Project Tracking Tools

- GitHub Issues — all development tasks, bugs, and features tracked as issues

- GitHub Projects (Kanban board) — sprint planning and progress tracking

- Notion — project documentation, meeting notes, and decision log

- Google Sheets — financial tracking, budget vs actuals, client pipeline

- Slack or WhatsApp — daily communication with advisors and pilot firms

- Loom — async video updates for investors and remote advisors

## 7.3 Change Management

Any change to project scope, timeline, or budget that exceeds 10% variance from this plan must follow this process:

- Change request documented in writing with reason, impact analysis, and proposed solution

- Impact assessed against timeline, budget, and quality — three constraints reviewed simultaneously

- If change affects investor commitments or seed funding use — investor notification required within 48 hours

- Approved changes documented in a change log with version number and date

- This project plan document updated within one week of any approved change

# 8. Success Criteria and KPIs

## 8.1 Project Success Criteria

Definition of Project Success URITHI version 1.0 is considered successfully delivered when: the platform is live in production, 3 pilot law firms have completed onboarding, the first paid client conversion has occurred, and the platform is operating without critical bugs for 30 consecutive days.

## 8.2 Key Performance Indicators — Tracked Monthly

| KPI | Month 3 | Month 6 | Month 9 | Month 12 |
| --- | --- | --- | --- | --- |
| Paying clients | 0 (pilot) | 3 | 7 | 10 |
| Monthly recurring revenue (MRR) | UGX 0 | UGX 4.5M | UGX 10.5M | UGX 14.7M |
| Active trusts on platform | 5 (pilot) | 30 | 80 | 120 |
| Distributions processed (UGX) | UGX 5M | UGX 80M | UGX 350M | UGX 600M |
| API uptime | 99% | 99.5% | 99.9% | 99.9% |
| Monthly churn rate | — | < 5% | < 3% | < 2% |
| Net Promoter Score (NPS) | — | 50+ | 60+ | 65+ |
| Website monthly visitors | 200 | 700 | 1,500 | 2,000 |
| Demo conversion rate | — | 30% | 28% | 25% |
| Critical bugs in production | 0 | 0 | 0 | 0 |

## 8.3 Technical Quality Gates

Before any deployment to production, the following quality gates must all pass:

- All automated tests passing (pytest, Vitest, Playwright) — zero failures

- Code coverage above 80% for backend services

- No critical or high severity security vulnerabilities from latest scan

- API response time below 500ms at 95th percentile under load test

- Mobile app startup time below 3 seconds on mid-range Android device

- All environment variables verified correct for production

- Database migration scripts tested and rolled back successfully on staging

- Backup and restore procedure verified within last 7 days

________________________________________________________________________________

URITHI Technologies Limited  |  Project Plan v1.0  |  April 2026

urithi.io  |  jaja@urithi.io  |  Kampala, Uganda

Confidential — Do not distribute without written permission